## Slide 1: Project Planning Lightning Talk
sdmay25-26 Bryce Rega, Marek Jablonski, Gavin Patel, Jonah Frosch, Long Yu Cost-Effective and Easily Configurable High Voltage Motor Controllers for Automotive Use
October 15th, 2024

## Slide 2: Project Overview
Custom High Voltage Motor Controller
Low Total cost for controller when compared to market options
Develop a GUI for interfacing and configuring controller
Compatible with many different applications

## Slide 3: In this project will we be designing the architecture and implementation of a motor controller for lightweight automotive use.

## Slide 4: Project Management Style
Waterfall and Agile hybrid for hardware
  Revisiting of previous work may be required
  Hardware design is a more rigid process
  Overall a more streamlined design process
Agile for software development
  Plan features to be added
  Better suited for our development structure
  A more fluid work process, no A to B steps

## Slide 5: Task Decomposition
Research
  Select dev board and software prep
  Research components
Prototyping
  Develop and test software on dev board
  Create schematic, then layout of PCB
  Prototype software for custom PCB
Minimum Viable Product (MVP)
  Hardware is functional and tested
  Software is functional and tested
  Revision 1 (MVP) is complete

## Slide 6: Milestones and Metrics
Development Board Controls Motor
  Motor is visibly spinning in the correct direction
  Current control has expected results
    Some percentage of throttle equals the measured current over the maximum current
Custom PCB Controls Motor
  Using the same metrics as above
  CAN input results in motor responding
  CAN output is read and accurate with CAN receiver (CAN Pi)
  Efficiency is measured by comparing idle power at a given speed on same motor with to an existing controller
PID RPM Functions
  Accuracy is measured using tachometer and input RPM

## Slide 7: Handling Risk
Additional Resources Required
  Likelihood: Low
  Mitigation: Proper project planning and research
Tasks taking longer than anticipated
  Likelihood: High
  Mitigation: Flexibility in planning
Scope Creep
  Likelihood: Medium
  Mitigation: Tiered requirements in end results

## Slide 8: Conclusion
We aim to develop a motor controller that applies to multiple applications. This required us to make a lightweight motor controller affordable, easy to use and adapt, and have plug-in diagnostics for troubleshooting. This can be developed into a set of milestones with specific metrics to gauge our progress.